Project Planning Phase

Project Planning (Product Backlog, Sprint Planning, Stories, Story Points)

| Date | 25 June 2026 |
| --- | --- |
| Name | VARSHINI S |
| Project Name | Metro Ticket Generating System in ServiceNow |
| Maximum Marks | 5 Marks |

- Product Backlog, Sprint Schedule, and Estimation

The following product backlog defines the planned development activities, user stories, sprint allocation, and story point estimation for the Metro Ticket Generating System developed using the ServiceNow platform.

| Sprint | User Story ID | User Story | Story Points | Priority |
| --- | --- | --- | --- | --- |
| Sprint 1 | USM-1 | Create Metro Ticket Service Catalog Item | 2 | High |
| Sprint 1 | USM-2 | Configure Catalog Variables and Mandatory Fields | 3 | High |
| Sprint 1 | USM-3 | Design Service Portal Form | 2 | High |
| Sprint 2 | USM-4 | Create Metro Station's Details Custom Table | 3 | High |
| Sprint 2 | USM-5 | Implement Flow Designer Automation | 5 | High |
| Sprint 2 | USM-6 | Configure ACLs for Secure Access | 2 | Medium |
| Sprint 3 | USM-7 | Test Service Portal and Mandatory Validations | 3 | High |
| Sprint 3 | USM-8 | Verify Request Tracking (REQ, RITM, SCTASK) | 2 | Medium |
| Sprint 3 | USM-9 | QR Code Integration and Final Documentation | 5 | Medium |

- Burndown Chart & Progress Metrics

A burndown chart was used to monitor the completion of planned work during each sprint. Story Points were reduced as development tasks were completed, helping track overall project progress.

Sprint-1 Burndown Analysis

- Starting Baseline: 7 Story Points.

- Mid-Sprint Status (Day 5): Successfully completed the Service Catalog creation, catalog variables configuration, and Service Portal form design.

- Sprint Closure: Sprint-1 concluded successfully with all planned tasks completed on schedule and no pending user stories.

Sprint-2 Burndown Analysis

- Starting Baseline: 10 Story Points.

- Mid-Sprint Status (Day 5): Minor delays occurred while configuring Flow Designer variable mapping and validating data storage in the custom Metro Station's Details table.

- Sprint Closure: Flow configuration and ACL implementation were completed after resolving mapping issues. Sprint-2 finished with all planned work completed.

Sprint-3 Burndown Analysis

- Starting Baseline: 10 Story Points.

- Mid-Sprint Status (Day 5): Completed Service Portal testing, mandatory field validation, and request tracking verification.

- Sprint Closure: Documentation, screenshots, and final testing were completed. QR Code generation was partially implemented as a planned enhancement.

- Individual Sprint Retrospective

A retrospective was conducted after each sprint to evaluate development progress, identify challenges, and improve future planning.

What Went Well

- Successfully implemented the Service Catalog, Service Portal, Flow Designer, Custom Tables, and Access Control Lists using ServiceNow's low-code platform.

- Flow Designer automation reduced manual effort in processing metro ticket requests.

- Mandatory field validation improved data accuracy and prevented incomplete submissions.

- Request tracking through REQ, RITM, and Catalog Task records was successfully verified.

What Could Be Improved

- QR Code generation requires additional API integration and testing.

- Variable mapping between catalog variables and the custom table required additional debugging.

- More time should be allocated for integration testing and advanced automation features.

Action Items for the Next Phase

- Complete QR Code generation and integrate ticket verification.

- Implement Email and SMS notifications for successful ticket booking.

- Add Metro Card Recharge functionality.

- Integrate an Online Payment Gateway.

- Develop Travel Analytics and Reporting Dashboard.

- Perform User Acceptance Testing (UAT) with multiple booking scenarios.